## PDCR - Blank
Supplier Process / Design Change Request (PDCR)
Note: Use this Change Notice and/or approval request to describe the product/process change that you wish to have considered for approval. Submit to the appropriate Supply Chain representative(s).
Change Type (circle one): Process Design Software
Allegion PCR#:
Vendor Change #:
Title of Request:
Supplier Name / Originator:
Origination Date:
Description of Change
Reason for Change
Benefit to Allegion
Affected Product(s)
Supplier: Allegion:
Affected Component(s)
Allegion / AMSTD Part #: Part Description: Allegion Location(s): Annual Usage: Pre-change Inventory on hand at Supplier:
Affected Process(es), if known
Supplier: Allegion:
Risks / Containment Actions
Supplier: Allegion:
Qualification, Validation Plan and Results
Schedule
(Min. Req’t: Expected Implementation Date, Date-code of first product affected and Min/Max timing to implement and validate)
Additional Information
Allegion Approvals (work authorization to proceed to next review )
Engineering: Date:
Quality: Date:

## PDCR - Example
Supplier Process / Design Change Request (PDCR)
Note: Use this Change Notice and/or approval request to describe the product/process change that you wish to have considered for approval. Submit to the appropriate Supply Chain representative(s).
Change Type (circle one): Process Design Software
Allegion PCR#: 2014-001, This is Allegion's internal tracking number
Vendor Change #: This is the supplier's internal tracking number for their convenience
Title of Request: Injection Molding Raw Material Equipment Change / Quality Improvement
Supplier Name / Originator: ABC Molding / John Doe - Quality Manager
Origination Date: January 15, 2014
Description of Change
¨ Change to new material dryer with 25kg hopper and with a new drying temperature of 235oF
Reason for Change
¨ Material dryer can only hold 10kg of material. Due to usage rate of material, drying time is too short. This causes splay, voids, and other defects. Original material drying temp. = 225oF
Benefit to Allegion
¨ Improved quality, will eliminate splay and voids. No effect on part's physical characteristics.
Affected Product(s)
¨ Supplier: Relays ¨ Allegion: Voyager 2
Affected Component(s)
Allegion / AMSTD Part #: ABC123456-098DD Part Description: Widget Allegion Location(s): Clarksville, Lexington, Tyler, and Waco Annual Usage: 325,000 Pre-change Inventory on hand at Supplier: 1,000 old style in inventory. These will be 100% visually sorted prior to shipping to Allegion.
Affected Process(es), if known
- Supplier: Injection Molding - Allegion: Voyager 2 assembly line
Risks / Containment Actions
- Supplier: None - Allegion: None
Qualification, Validation Plan and Results
- Will 100% visually sort first 100pcs looking for splays and voids. If problems are found then an Early Launch Containment (ELC) Plan will be developed.
Schedule
(Min. Req’t: Expected Implementation Date, Date-code of first product affected and Min/Max timing to implement and validate) - Equipment change (1wk install) - 3/1/07 - Begin 100 piece visual confirmation (1st Production Run) - 3/2/07 - Delivery of 1st shipment to Allegion - 3/15/07
Additional Information
- None
Allegion Approvals (work authorization to proceed to next review )
Engineering: Doug Doright Date: 1/13/14
Quality: Jason Goforward Date: 1/12/14
EXAMPLE